# The 90-Day AI Workbook

Draft v2 · 22 July 2026 · The leave-behind for the 90-Day Engagement

A working document for the leadership team. It starts life in the $1,900 AI Working Session, gets filled in across the 90-Day Engagement, and stays in the business when Jeanna steps back. Not a report about the client; a document the client writes, with Jeanna beside them. Part A is the workbook; Part B is the governance pack the business adopts along the way (policy template, staff one-pager, rollout checklist).

Sources combined (for Jeanna’s reference, not for the client copy): - The AI Policy Starter Pack in full (Products/AI Policy Pack/drafts/, built 4 July 2026): the AI Usage Policy template with its “why this matters” teaching notes, the NIST AI RMF four steps in plain English, the risk and speed grid, the four tests, the ten-question security self-assessment, the incident plan, the staff one-pager, the ten-step rollout checklist and the adviser questions. This is the governance work from the niche-product experiment after Lauren Dallas’s 30 June webinar; SEMrush put “ai policy template” at 50 searches a month in AU, and it was redirected to training material. Folding it in here gives it the distribution it deserved: inside a $15,000 engagement instead of behind a $129 checkout. All Vooee IP, reused freely. - The AI Enabled Leader participant workbooks (readiness snapshot, governance responsibility matrix, opportunity mapping, better-questions review, journal pattern). Copyright BetterHRx and Beth Barratt-Browne. Concepts adapted in fresh wording below; Jeanna to confirm what the partnership terms allow before anything closer than adaptation. - Section’s 1-Year AI Enablement Checklist (30/90/365 staging, benchmarks, cut vs create). Cited where quoted, structure not copied. - Vooee’s own 4D framework and engagement structure.

# Part A · The workbook

## How to use this workbook

One copy, owned by one person, written in by the whole leadership team. Sections 1 and 2 are filled in during the Working Session. Sections 3 to 5 are worked through across the ninety days. Section 6 is yours to keep running after that. If a page stays blank, that is information too; bring it to the next working session.

## Section 1 · Where we are (Working Session, first hour)

The business: ______________ Accountable owner for AI: ______________ Engagement start: ______________ Day 90 lands on: ______________

### Honest baseline

Each leader answers separately, then compare. 1. What would you love AI to take off your plate? 2. What worries you about it, honestly? 3. Where is the business most exposed if we get this wrong? 4. Confidence leading AI change, 1 to 10, and why that number.

### The snapshot

Score each area now, in pencil. You will score it again at day 90.

| Area | Today (1 to 10) | Day 90 | What the score is telling us |
| --- | --- | --- | --- |
| Leadership agreement on what AI is for |  |  |  |
| Ground rules (who decides, what is off limits) |  |  |  |
| Trust (do people feel safe saying they use AI?) |  |  |  |
| Capability (can people use it well, not just use it?) |  |  |  |
| Tools and data (right tools, safe data) |  |  |  |
| Commercial value (is it showing up in the work?) |  |  |  |

A note from the research: only around 1% of executives call their organisation AI mature, and the constraint they name is leadership, not technology (McKinsey, 2025). Low scores here are normal. Unexamined scores are the risk.

### Our AI position, in one paragraph

Why does this business want AI at all? Write it in plain language a new hire would understand. If five leaders would write five different paragraphs, that is the first thing the ninety days fixes.

One deliberate choice: is AI here mainly to save time or mainly to grow the business? (You can want both; choose which one gets the first ninety days.) Section calls this cut vs create; the point is to stop the strategy being everything at once.

### Decisions that stay human

List the decisions AI never makes in this business, whatever the tool promises. Hiring, pricing exceptions, client advice, anything touching health or money or reputation. Short list, absolute. 1. ______________________________________________ 2. ______________________________________________ 3. ______________________________________________

## Section 2 · The ground rules (days 1 to 30)

This is the Govern step of the NIST AI Risk Management Framework, the international standard this workbook quietly follows. You do not need to know the framework; the four sections track its four functions.

### Who owns what

Ambiguity is the actual risk. Names, not roles.

| Question | Name | Where it is written down |
| --- | --- | --- |
| Who owns AI decisions? |  |  |
| Who owns AI risk and incidents? |  |  |
| Who owns the policy and keeps it current? |  |  |
| Who owns the people side (training, concerns, morale)? |  |  |

### What tools are we actually using?

Ask everyone what they have used for work in the past month, personal accounts included. Expect surprises; that is the point of asking.

| Tool | Who uses it | Approved / parked / no |
| --- | --- | --- |

### The hard lines

Five “we do not” rules. Edit to this business, keep them short, keep them absolute. 1. We do not put client-identifying information into unapproved tools. 2. We do not send AI-written work to a client without a human reading it and owning it. 3. We do not ______________________________________________ 4. We do not ______________________________________________ 5. We do not ______________________________________________

### Where do we need a human gate?

Place every AI use on this grid. Most will sit bottom-left; that is fine, leave them alone. The top-right corner is where rules come before launch, not after the first incident.

|  | Human in the loop anyway | Acts before a human sees it |
| --- | --- | --- |
| High stakes (money, health, hiring, advice, reputation) | Human approves every single time | Guardrails and a kill switch before go-live |
| Low stakes (internal, recoverable) | Spot-check weekly | Review monthly |

### What this month produces

By day 30 the business has an adopted AI Usage Policy: the template in Part B, brackets filled in during the working sessions, reviewed by the business’s own adviser, dated and owned. The staff one-pager (also Part B) goes on the wall, and the team gets its fifteen-minute walkthrough. The ten-step rollout checklist in Part B is the runsheet; steps 1 to 8 belong to this month, steps 9 and 10 are Sections 4 and beyond.

## Section 3 · Build and prove (days 31 to 60)

### Choosing what to build

For each candidate project, answer five questions before anyone opens a tool. The fifth is the one that saves you money. 1. What problem are we solving? 2. What value does it create, and how would we measure it? 3. What capability does it build in our people? 4. What risk does it carry, and can we govern it with the grid above? 5. What are we deliberately choosing not to pursue this quarter?

### Where the effort goes

AI effort tends to pool at individual productivity and stall there. Note where each project sits; make sure at least one lives above the first row.

| Level | Project | Owner |
| --- | --- | --- |
| One person’s work |  |  |
| A team’s work |  |  |
| A whole function |  |  |
| The business itself |  |  |

### The four tests

Before trusting any tool with something that matters. Skip for bottom-left-grid uses.

| Test | The question | Pass looks like |
| --- | --- | --- |
| Functional | Does it do the job? | Ten real examples from our business, done correctly |
| Compliance | Does it follow our rules? | Data handled per our policy; outputs meet our sector’s requirements |
| Adversarial | What happens at the edges? | Fed the weird cases, it fails safely, not confidently |
| Scenario | Does it survive a real week? | Run in parallel with the normal process before switching |

Keep a one-line record of what was tested. That record is what makes diligence visible to a client, an insurer, or an adviser.

### The security check

Ten questions, yes / no / not sure. Every no and not sure goes on the action list. (Identify: do we know every tool in use, and what data each can see? Protect: strong passwords and MFA on work AI accounts; sensitive data kept out of unapproved tools. Detect: would we notice a tool doing something wrong; does someone check automations on a schedule? Respond: does everyone know who to tell, same day; do we know when a slip becomes a notifiable breach? Recover: could we operate with the tool switched off; after an incident, do we change something?)

Score: ____ / 10 yes · Action list started: ☐

## Section 4 · Make it stick (days 61 to 90)

### The routine

- Every client-facing output read by a person who owns it. No exceptions; this is the one rule that never bends.

- Spot-check frequencies from the grid (weekly for drafts, monthly for automations).

- A quarterly look at what tools have access to; a policy review every six months.

### The bad day

Four moves, on the wall: stop → tell → assess → fix and record. Pre-brief the adviser on when a data slip becomes a notifiable breach under the Privacy Act; deadlines apply, and mid-incident is the wrong time to learn them.

### Champions and the library

- Who are our two or three AI champions (the people others actually ask)? ______________

- Where do working prompts, projects and workflows live so they outlast the person who built them? ______________

- What is our version of showing the work: a monthly show-and-tell, a shared channel, five minutes in the team meeting? ______________

### The numbers we will watch

Enterprise benchmarks, translated to our size (Section, 2026, cited for context, not worship): - Using it weekly: how many of us touch AI in real work every week? (Their bar: 80% of the workforce.) - Using it well: how many could show someone else a working workflow, not just a chat window? (Their bar: 80% proficient, 20% expert.) - Something always running: does each person have at least one task quietly handled in the background?

| Measure | Day 0 | Day 90 |
| --- | --- | --- |
| People using AI weekly in real work | / | / |
| People who could teach one workflow | / | / |
| Background tasks running |  |  |

## Section 5 · Day 90, honestly

Re-score the snapshot in Section 1, same pencil, same honesty. Then: - What moved the most, and what moved it? - What did not move, and is that a problem or a choice? - One thing worth scaling next quarter: ______________ - One risk that scaling would create: ______________ - One commitment leadership makes for the next ninety days: ______________

The engagement ends here. The workbook does not.

## Section 6 · The running pages (after Jeanna steps back)

A page per month, three lines each, kept by the accountable owner: - One action we took: ______________ - One conversation we had: ______________ - One question for next month: ______________

When three months of pages look the same, book a working session; that is what plateau looks like.

# Part B · The governance pack

The three documents below slot in verbatim from Products/AI Policy Pack/drafts/ (one source of truth; don’t fork the text into this file):

- The AI Usage Policy template (01-ai-usage-policy-template.md, ~10pp). Twelve sections, every [bracket] a leadership decision, with the grey “why this matters” notes kept in: purpose and scope, accountability, approved tools, acceptable use with the five hard no’s, data rules (APP 8, onshore processing), telling clients, human review, security basics, the four-move incident plan, training, review cadence, definitions. In the engagement this is filled in live during the day 1 to 30 sessions rather than alone on a weekend; the “why this matters” notes become talking points, which is what they always wanted to be.

- The staff one-pager (03-staff-one-pager-and-rollout-checklist.md, page 1). Do / Don’t / Unsure, prints A4 for the wall. Filled in from the adopted policy at the day-30 mark.

- The ten-step rollout checklist (same file, page 2). Becomes the engagement runsheet for month one; steps 9 (set the routine) and 10 (train for fluency) hand over to workbook Sections 4 and 6.

One edit needed for the engagement version: the pack’s clause 10 and checklist step 10 plug “Vooee’s Working with AI programme” as the fluency path. Inside the 90-Day Engagement that reads like an ad for something the client already bought; repoint it to the coaching happening inside the engagement itself.

The pack’s fourth document (04-customise-with-ai-prompt-sheet.md) stays out of the leave-behind; it is the self-serve substitute for having Jeanna in the room, which this client has.

## The fine print

This workbook is general information and an educational starting point, not legal advice. Before adopting any policy it touches, have it reviewed by a qualified legal or HR professional who knows the business and sector. Frameworks referenced: NIST AI Risk Management Framework; the National AI Centre’s voluntary responsible AI practices; benchmarks cited from Section (sectionai.com) and McKinsey with attribution.

© Vooee Pty Ltd · vooee.au

# Production notes (not part of the client document)

- IP check before this ships: the readiness snapshot, ownership matrix, opportunity levels and journal pattern are adapted, reworded and restructured from the AI Enabled Leader workbooks (BetterHRx and Beth Barratt-Browne). The adaptation is substantial, but Jeanna should confirm the partnership terms, or simply confirm Beth is comfortable, before this is client-facing. The NIST material is Vooee’s own Policy Pack work and carries no such question.

- The Policy Pack question is now a product decision. The pack’s whole content lives inside this leave-behind (Part B verbatim, quick-start material woven through Part A). Options: (a) retire the $129 pack and let the governance work live only inside engagements, (b) keep both, with the pack as the self-serve rung below the Working Session (its webinar funnel “AI ground rules for Australian small business” then feeds the advisory ladder). The 4 July kill gates were never run; this is the moment to decide, and (b) costs nothing extra since the drafts are done.

- Format: A4 Word or fillable PDF, vooee branding, generous white space for handwriting. The snapshot and grid pages want a full page each. Cover carries client name and dates like a logbook.

- The pencil rule: day-0 and day-90 scores in the same table is the whole emotional arc of the leave-behind; keep them side by side in any redesign.

- What was deliberately left out: Section’s agents-per-employee ratio (hype-adjacent for this audience), the six-domain “AI Readiness Index” language (too corporate for vooee’s voice), and any trademark-style naming of frameworks. The 4D framework gets its mention through the coaching, not this document.